## Sheet2
| Unique ID | User story | Story Points | Asignee | Reviewer 1 | Reviewer 2
1. Admin | 1.1 | As an admin I should be able to sign in so that I can access my profile | 3 | Kariman | Islam
| 1.2 | As an admin I should be able to view my profile | 3 | Saad | Shahd
| 1.3 | As an admin I should be able to update my profile | 5 | Saad | Peter
| 1.4 | As an admin I should be able to delete my profile | 5 | Saad | Karim
| 1.5 | As an admin I should be able to accept projects | 3 | Gabry | Ashraf
| 1.6 | As an admin I should be able to view awaiting approval projects | 3 | Gabry | Hossam
| 1.7 | As an admin I should be able to view a project by it's id | 3 | Gabry | Kariman
| 1.8 | As an admin I should be able to view awaiting approval tasks | 3 | Gabry | Marwan
| 1.9 | As an admin I should be able to view all projects | 3 | Gabry | Farah
| 1.10 | As an admin I should be able to view all tasks of a certain project by project id | 3 | Gabry | Hossam
| 1.11 | As an admin I should be able to view all tasks | 5 | Gabry | Saad
| 1.12 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | Islam | Gabry
| 1.13 | As an admin I should be able to update task attributes | 5 | Islam | Kariman
| 1.14 | As an admin I should be able to delete projects | 5 | Kariman | Shahd
| 1.15 | As an admin I should be able to delete tasks | 5 | Kariman | Farah
| 1.16 | As an admin I should be able to search for tasks by their name | 5 | Peter | Hossam
| 1.17 | As an admin I should be able to search for projects by their name | 5 | Peter | Ashraf
| 1.18 | As an admin I should be able to search projects by project name | 5 | Peter | Marwan
| 1.19 | As an admin I should be able to create a certificate so that candidates can apply for them | 3 | Shahd | Karim
| 1.20 | As an admin I should be able to view all certificates | 3 | Shahd | Farah
| 1.21 | As an admin I should be able to view a certificate by its id | 5 | Shahd | Hossam
| 1.22 | As an admin I should be able to update a certificate | 5 | Shahd | Ashraf
| 1.23 | As an admin I should be able to delete a certificate | 5 | Shahd | Kariman
| 1.24 | As an admin I should be able to search certificates by certificate name | 5 | Peter | Gabry
| 1.25 | As an admin I should be able to create an evaluation tests for the certificates | 3 | Karim | Ashraf
| 1.26 | As an admin I should be able to view all evaluation tests for the all certificates | 3 | Karim | Islam
| 1.27 | As an admin I should be able to view all evaluation tests for the a certain certificate by certificate id | 3 | Karim | Saad
| 1.28 | As an admin I should be able to view a certain test for the a certain certificate by certificate id and test id | 5 | Karim | Islam
| 1.29 | As an admin I should be able to update evaluation tests for certificates | 5 | Karim | Hossam
| 1.30 | As an admin I should be able to delete evaluation tests for certificates | 3 | Karim | Peter
| 1.31 | As an admin I should be able to view candidates' evaluation for certificate so that I can accept candidates | 3 | Karim | Marwan
| 1.32 | As an admin I should be able to add a certificate to candidates' profiles if they passed the evaluation | 5 | Karim | Farah
| 1.33 | As an admin I should be able to search all partners by their names | 5 | Peter | Karim
| 1.34 | As an admin I should be able to search all candidates by their names | 5 | Peter | Shahd
| 1.35 | As an admin I should be able to search all consultancies by their names | 5 | Peter | Hossam
| 1.36 | As an admin I should be able to search all researches by their title | 5 | Peter | Ashraf
| 1.37 | As an admin I should be able to search all reports by their title | 5 | Peter | Gabry
| 1.38 | As an admin I should be able to create announcements | 3 | Farah | Saad
| 1.39 | As an admin I should be able to view all announcements | 3 | Farah | Marwan
| 1.40 | As an admin I should be able to view a certain announcement by id | 3 | Farah | Kariman
| 1.41 | As an admin I should be able to update announcements | 5 | Farah | Shahd
| 1.42 | As an admin I should be able to delete announcements | 5 | Farah | Islam
| 1.43 | As an admin I should be able to view all reports posted by consultancies | 3 | Marwan | Peter
| 1.44 | As an admin I should be able to view all researches posted by consultancies | 3 | Marwan | Karim
| 1.45 | As an admin I should be able to view a certain report posted by consultancies by report id | 3 | Marwan | Hossam
| 1.46 | As an admin I should be able to view a certain research posted by consultancies by research id | 3 | Marwan | Islam
| 1.47 | As an admin I should be able to logout to leave my page | 3
2. Partner | 2.1 | As a partner I should be able to sign up so that I can create an account | 3 | Islam | Shahd
| 2.2 | As a partner I should be able to sign in so that I can access my profile | 3 | Kariman | Saad
| 2.3 | As a partner I should be able to view my profile | 3 | Saad | Ashraf
| 2.4 | As a parner I should be able to update my profile | 5 | Saad | Gabry
| 2.5 | As a partner I should be able to delete my profile | 5 | Saad | Marwan
| 2.6 | As a partner I should be able to create projects so that admin can view them to accept or reject them | 3 | Kariman | Hossam
| 2.7 | As a partner I should be able to create tasks so that admin can view them to accept or reject them | 3 | Kariman | Karim
| 2.8 | As a partner I should be able to view all awaiting approval projects | 3 | Ashraf | Peter
| 2.9 | As a partner I should be able to view a project by its id | 3 | Ashraf | Farah
| 2.10 | As a partner I should be able to view awaiting approval tasks | 3 | Ashraf | Islam
| 2.11 | As a partner I should be able to view approved projects | 3 | Ashraf | Shahd
| 2.12 | As a partner I should be able to view all approved tasks for my project by project id | 3 | Ashraf | Kariman
| 2.13 | As a partner I should be able to view a certain task by its id | 3 | Ashraf | Saad
| 2.14 | As a partner I should be able to update projects before it gets approved by the admin | 5 | Hossam | Ashraf
| 2.15 | As a partner I should be able to update tasks before it gets approved by the admin | 5 | Hossam | Gabry
| 2.16 | As a partner I should be able to delete projects before it gets approved by the admin | 5 | Hossam | Marwan
| 2.17 | As a partner I should be able to delete tasks before it gets approved by the admin | 5 | Hossam | Farah
| 2.18 | As a partner I should be able to search for tasks by their name | 5 | Peter | Karim
| 2.19 | As a partner I should be able to search for projects by their name | 5 | Peter | Hossam
| 2.20 | As a partner I should be able to view all consultancies applying for my project | 3 | Hossam | Peter
| 2.21 | As a partner I should be able to view the consultancy working on my project | 3 | Hossam | Gabry
| 2.22 | As a partner I should be able to accept a certain consultancy applying for my project | 3 | Hossam | Ashraf
| 2.23 | As a partner I should be able to view all candidates applying for a task inside my project | 3 | Hossam | Kariman
| 2.24 | As a partner I should be able to accept candidates applying for tasks inside my project | 3 | Hossam | Islam
| 2.25 | As a partner I should be able to view a certain candidate working on a certain task inside my project | 3 | Hossam | Shahd
| 2.26 | As a partner I should be able to view all reports posted by consultancies | 3 | Karim | Saad
| 2.27 | As a partner I should be able to view all researches posted by consultancies | 3 | Karim | Farah
| 2.28 | As a partner I should be able to view a certain report posted by consultancies by report id | 3 | Karim | Marwan
| 2.29 | As a partner I should be able to view a certain research posted by consultancies by research id | 3 | Karim | Hossam
| 2.30 | As a partner I should be able to view all announcements | 3 | Farah | Islam
| 2.31 | As a partner I should be able to view a certain announcement by announcement id | 3 | Farah | Shahd
| 2.32 | As a partner I should be able to search all partners by their names | 5 | Peter | Kariman
| 2.33 | As a partner I should be able to search all candidates by their names | 5 | Peter | Saad
| 2.34 | As a partner I should be able to search all consultancies by their names | 5 | Peter | Gabry
| 2.35 | As a partner I should be able to search all researches by their title | 5 | Peter | Ashraf
| 2.36 | As a partner I should be able to search all reports by their title | 5 | Peter | Hossam
| 2.37 | As a partner I should be able to search all certificates by their names | 5 | Peter | Karim
| 2.38 | As a partner I should be able to logout to leave my page | 3
3. Candidate | 3.1 | As a candidate I should be able to sign up so that I can create an account | 3 | Islam | Farah
| 3.2 | As a candidate I should be able to sign in so that I can access my profile | 3 | Kariman | Marwan
| 3.3 | As an candidate I should be able to view my profile | 3 | Saad | Islam
| 3.4 | As an candidate I should be able to update my profile | 5 | Saad | Peter
| 3.5 | As an candidate I should be able to delete my profile | 5 | Saad | Shahd
| 3.6 | As a candidate I should be able to view recommended tasks that I can apply for according to my set of skills sorted by their posting date to apply for them | 3 | Gabry | Kariman
| 3.7 | As a candidate I should be able to view awaiting approval tasks sorted by their posting date to apply for them | 3 | Gabry | Ashraf
| 3.8 | As a candidate I should be able to view all approved tasks sorted by their posting date to apply for them | 3 | Gabry | Farah
| 3.9 | As a candidate I should be able to view main project of my task | 3 | Ashraf | Marwan
| 3.10 | As a candidate I should be able to view a certain task by its id | 3 | Ashraf | Gabry
| 3.11 | As a candidate I should be able to apply for tasks that fit my skills so that the partner or consultancies views my application | 3 | Ashraf | Karim
| 3.12 | As a candidate I should be able to disapply for tasks I applied for before they get approved by partner or consultancy | 3 | Ashraf | Hossam
| 3.13 | As a candidate I should be able to update the task lifecycle so that the partner or the consultancy can keep track of the workflow | 5 | Marwan | Peter
| 3.14 | As a candidate I should be able to search for all tasks by their name | 5 | Peter | Islam
| 3.15 | As a candidate I should be able to search for all projects by their name | 5 | Peter | Shahd
| 3.16 | As a candidate I should be able to request a new certificate | 5 | Kariman | Kariman
| 3.17 | As a candidate I should be able to view all certificates so that I can apply for them | 3 | Shahd | Farah
| 3.18 | As a candidate I should be able to view all recommended certificates so that I can apply for them | 3 | Shahd | Marwan
| 3.19 | As a candidate I should be able to view a certain certificate by its id | 3 | Shahd | Saad
| 3.20 | As a candidate I should be able to apply for a certificate by its id so that I can get evaluated | 3 | Shahd | Gabry
| 3.21 | As a candidate I should be able to view evaluations for a certificate that I applied for | 3 | Marwan | Ashraf
| 3.22 | As a candidate I should be able to take evaluations for a certificate that I applied for | 5 | Marwan | Hossam
| 3.23 | As a candidate I should be able to submit evaluations for a certificate that I applied for so that admin can view the evaluations | 3 | Marwan | Karim
| 3.24 | As a candidate I should be able to update my set of skills after having a certain certificate | 5 | Islam | Peter
| 3.25 | As a candidate I should be able to view all reports posted by consultancies | 3 | Kariman | Islam
| 3.26 | As a candidate I should be able to view all researches posted by consultancies | 3 | Kariman | Shahd
| 3.27 | As a candidate I should be able to view a certain report posted by consultancies by report id | 3 | Kariman | Farah
| 3.28 | As a candidate I should be able to view a certain research posted by consultancies by research id | 3 | Kariman | Gabry
| 3.29 | As a candidate I should be able to view all announcements | 3 | Farah | Ashraf
| 3.30 | As a candidate I should be able to view a certain announcement by announcement id | 3 | Farah | Kariman
| 3.31 | As a candidate I should be able to search for certificates by their name | 5 | Peter | Hossam
| 3.32 | As a candidate I should be able to search all partners by their names | 5 | Peter | Karim
| 3.33 | As a candidate I should be able to search all candidates by their names | 5 | Peter | Saad
| 3.34 | As a candidate I should be able to search all consultancies by their names | 5 | Peter | Islam
| 3.35 | As a candidate I should be able to search all researches by their title | 5 | Peter | Gabry
| 3.36 | As a candidate I should be able to search all reports by their title | 5 | Peter | Ashraf
| 3.37 | As a candidate I should be able to logout to leave my page | 3 | Peter | Hossam
4. Consultancy | 4.1 | As a consultant I should be able to sign up so that I can create an account | 3 | Islam | Karim
| 4.2 | As a consultant I should be able to sign in so that I can access my profile | 3 | Kariman | Shahd
| 4.3 | As an consultant I should be able to view my profile | 3 | Saad | Farah
| 4.4 | As an consultant I should be albe to update my profile | 5 | Saad | Kariman
| 4.5 | As an consultant I should be able to delete my profile | 5 | Saad | Islam
| 4.6 | As a consultant I should be able to create tasks so that candidates can apply for them | 3 | Saad | Shahd
| 4.7 | As a consultant I should be able to view all projects | 3 | Gabry | Ashraf
| 4.8 | As a consultant I should be able to view all awaiting approval projects | 3 | Gabry | Farah
| 4.9 | As a consultant I should be able to view a certain project by its id | 3 | Gabry | Marwan
| 4.10 | As a consultant I should be able to view recommended projects that I can apply for | 3 | Gabry | Hossam
| 4.11 | As a consultant I should be able to view all tasks of my project | 3 | Gabry | Karim
| 4.12 | As a consultant I should be able to view a certain task by its id | 3 | Ashraf | Peter
| 4.13 | As a consultant I should be able to view approved projects | 3 | Ashraf | Gabry
| 4.14 | As a consultant I should be able to apply only for projects that requested by the partner to receive consulting and fits my set of skills so that I can divide it into tasks for candidates to apply for them | 3 | Ashraf | Islam
| 4.15 | As a consultant I should be able to disapply for projects I applied for before it gets approved by partner | 3 | Ashraf | Shahd
| 4.16 | As a consultant I should be able to view the main project of my task | 3 | Ashraf | Kariman
| 4.17 | As a consultant I should be able to update project attributes | 5 | Islam | Peter
| 4.18 | As a consultant I should be able to update tasks | 5 | Islam | Saad
| 4.19 | As a consultant I should be able to delete tasks | 5 | Islam | Gabry
| 4.20 | As a consultant I should be able to search for tasks by their name | 5 | Peter | Ashraf
| 4.21 | As a consultant I should be able to search for projects by their name | 5 | Peter | Hossam
| 4.22 | As a consultant I should be able to view all candidates applying for a task inside my project | 3 | Saad | Karim
| 4.23 | As a consultant I should be able to view a certain candidate working on a certain task inside my project | 3 | Saad | Farah
| 4.24 | As a consultant I should be able to accept candidates applying for tasks inside my project | 3 | Farah | Marwan
| 4.25 | As a consultant I should be able to request a new certificate | 5 | Kariman | Islam
| 4.26 | As a consultant I should be able to view all certificates so that I can apply for them | 3 | Shahd | Peter
| 4.27 | As a consultant I should be able to view all recommended certificates so that I can apply for them | 3 | Shahd | Ashraf
| 4.28 | As a consultant I should be able to view a certain certificate by its id | 3 | Shahd | Gabry
| 4.29 | As a consultant I should be able to apply for a certificate by its id so that I can get evaluated | 3 | Shahd | Karim
| 4.30 | As a consultant I should be able to view evaluations for a certificate that I applied for | 3 | Hossam | Peter
| 4.31 | As a consultant I should be able to take evaluations for a certificate that I applied for | 5 | Hossam | Islam
| 4.32 | As a consultant I should be able to submit evaluations for a certificate that I applied for so that admin can view the evaluations | 3 | Farah | Kariman
| 4.33 | As a consultant I should be able to update my set of skills after having a certain certificate | 5 | Islam | Karim
| 4.34 | As a consultant I should be able to search for certificates by their name | 5 | Peter | Farah
| 4.35 | As a consultant I should be able to create reports | 3 | Marwan | Ashraf
| 4.36 | As a consultant I should be able to view all reports | 3 | Marwan | Gabry
| 4.37 | As a consultant I should be able to view a report by its id | 3 | Marwan | Islam
| 4.38 | As a consultant I should be able to update report | 5 | Marwan | Saad
| 4.39 | As a consultant I should be able to delete report | 5 | Marwan | Gabry
| 4.40 | As a consultant I should be able to create researches | 3 | Islam | Ashraf
| 4.41 | As a consultant I should be able to update research | 5 | Islam | Peter
| 4.42 | As a consultant I should be able to view all researches | 3 | Islam | Hossam
| 4.43 | As a consultant I should be able to view a research by its id | 3 | Islam | Karim
| 4.44 | As a consultant I should be able to delete research | 5 | Farah | Saad
| 4.45 | As a consultant I should be able to view all announcements | 3 | Farah | Marwan
| 4.46 | As a consultant I should be able to view a certain announcement by announcement id | 3 | Farah | Shahd
| 4.47 | As a consultant I should be able to search all partners by their names | 5 | Peter | Kariman
| 4.48 | As a consultant I should be able to search all candidates by their names | 5 | Peter | Islam
| 4.49 | As a consultant I should be able to search all consultancies by their names | 5 | Peter | Ashraf
| 4.50 | As a consultant I should be able to search all researches by their title | 5 | Peter | Gabry
| 4.51 | As a consultant I should be able to search all reports by their title | 5 | Peter | Saad
| 4.52 | As an consultant I should be able to logout to leave my page | 3