## Sheet1
| Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1.Admin | 1.1 | As an admin I should be able to sign in so that I can access my profile | 8 |  | -
| 1.2 | As an admin I should be able to view the project description so that I can approve/disapprove it getting posted | 8 | Karim | 2.3 | Islam
| 1.3 | As an admin I should be able to create tasks/projects so that candidates can apply | 8 | Karim | 2.3 | Islam
| 1.4 | As an admin I should be able to delete tasks | 5 | Karim | 2.3 | Islam
| 1.5 | As an admin I should be able to update tasks | 5 | Karim | 2.3 | Islam
| 1.6 | As an admin I should be able to create project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 8 | Peter | 2.3 | Islam
| 1.7 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 8 | Peter | 2.3/1.6 | Islam
| 1.8 | As an admin I should be able to read candidates' applications so that I can choose an appropriate candidate | 5 | Peter | 3.7 | Farah
| 1.9 | As an admin I should be able to assign tasks to appropriate candidates so that they get notified with the task | 8 | Peter | 3.7 | Farah
| 1.10 | As an admin I should be able to read the candidates' evaluation so that they check the authenticity | 5 | Peter | 3.14 | Gabry
| 1.11 | As an admin I should be able to update the candidates' evaluation so that they receive the certification | 8 | Karim | 1.10 | Gabry
| 1.12 | As an admin I should be able to view my profile | 5 | Ahmed Hossam | 1.1(not in this sprint) | Gabry
| 1.13 | As an admin I should be able to update my profile | 8 | Ahmed Hossam | 1.1(not in this sprint) | Gabry
| 1.14 | As an admin I should be able to delete my profile | 8 | Ahmed Hossam | 1.1(not in this sprint) | Gabry
| 1.15 | As an admin I should be able to create project life cycle that includes all agreed upon steps so that the client views it everytime it gets updated | 8 | Ahmed Hossam | 1.9 | Karim
| 1.16 | As an admin I should be able to create messages to partners so that we are able to negotiate project description | 8 | Saad | 2.3 | Karim
| 1.17 | As an admin I should be able to view my messages | 5 | Saad | 1.16 | Karim
| 1.18 | As an admin I should be able to delete inbox messages | 8 | Saad | 1.16/1.17/1.19 | Karim
| 1.19 | As an admin I should be able to read messages from partners so that we are able to negotiate project description | 8 | Saad | 2.10 | Karim
| 1.20 | As an admin I should be able to create evaluations for certificates | 3 | Ahmed Ashraf | - | Peter
| 1.21 | As an admin I should be able to view the evaluations for certificates | 5 | Ahmed Ashraf | 1.20 | Peter
| 1.22 | As an admin I should be able to update evaluations for certificates | 5 | Ahmed Ashraf | 1.20/1.21 | Peter
| 1.23 | As an admin I should be able to delete evaluations for certificates | 5 | Ahmed Ashraf | 1.20/1.21 | Peter
| 1.24 | As an admin I should be able to create notifications to candidates | 5 | Marwan | - | Saad
| 1.25 | As an admin I should be able to delete notifications to candidates | 5 | Marwan | 1.24 | Saad
| 1.26 | As an admin I should be able to update notifications to candidates | 5 | Marwan | 1.24 | Saad
| 1.27 | As an admin I should be able to view notifications to candidates | 3 | Marwan | 1.24 | Saad
| 1.28 | As an admin I should be able to create project orientation invitation to accepted candidates | 5 | Shahd | 1.3 | Marwan
| 1.29 | As an admin I should be able to update project orientation invitation to accepted candidates | 3 | Shahd | 1.3/1.28 | Marwan
| 1.30 | As an admin I should be able to delete project orientation invitation to accepted candidates | 5 | Shahd | 1.3/1.28 | Marwan
| 1.31 | As an admin I should be able to view my project orientation invitation to accepted candidates | 3 | Shahd | 1.3/1.28 | Marwan
| 1.32 | As an admin I should be able to logout to leave my page | 3 |  | 1.1
2. PARTNER | 2.1 | As a partner I should be able to sign up so that I can create an account | 8 |  | -
| 2.2 | As a partner I should be able to sign in so that I can access my profile | 8 |  | 2.1(not in this sprint)
| 2.3 | As a partner I should be able to create a project description so that it gets viewed by the admin | 5 | Islam | - | Ahmed Ashraf
| 2.4 | As a partner I should be able to view my project description(s) | 3 | Islam | 2.3 | Ahmed Ashraf
| 2.5 | As a partner I should be able to update my project description(s) | 5 | Islam | 2.3 | Ahmed Ashraf
| 2.6 | As a partner I should be able to delete my project description(s) | 8 | Islam | 2.3 | Ahmed Ashraf
| 2.7 | As a partner I should be able to view my profile | 5 | Kariman | 2.2(not in this sprint) | Ahmed Ashraf
| 2.8 | As a partner I should be able to update my profile | 8 | Kariman | 2.2(not in this sprint) | Ahmed Hossam
| 2.9 | As a partner I should be able to delete my profile | 8 | Kariman | 2.2(not in this sprint) | Ahmed Hossam
| 2.10 | As a partner I should be able to create messages to admins so that we are able to negotiate project description | 13 | Kariman | 2.3 | Ahmed Hossam
| 2.11 | As a partner I should be able to view my messages | 13 | Kariman | 2.10 | Ahmed Hossam
| 2.12 | As a partner I should be able to read messages from admins so that we are able to negotiate project description | 13 | Islam | 1.16 | Ahmed Hossam
| 2.13 | As a partner I should be able to delete inbox messages | 8 | Saad | 2.10/2.11/2.12 | Farah
| 2.14 | As a partner I should be able to logout to leave my page | 3 |  | 2.2(not in this sprint)
3. CANDIDATE | 3.1 | As a candidate I should be able to sign up so that I can create an account | 8 |  | -
| 3.2 | As a candidate I should be able to sign in so that I can access my profile | 8 |  | 3.1(not in this sprint)
| 3.3 | As a candidate I should be able to view my profile | 5 | Farah | 3.2(not in this sprint) | Kariman
| 3.4 | As a candidate I should be able to update my profile | 8 | Farah | 3.2(not in this sprint) | Kariman
| 3.5 | As a candidate I should be able to delete my profile | 8 | Farah | 3.2(not in this sprint) | Kariman
| 3.6 | As a candidate I should be able to view tasks/projects to apply for them | 8 | Farah | 1.3 | Kariman
| 3.7 | As a candidate I should be able to apply for tasks/projects that fit my skills so that the admin views my application | 13 | Farah | 1.3/3.6 | Kariman
| 3.8 | As a candidate I should be able to search for tasks so that I can apply for them | 13 |  | 1.3(not in this sprint)
| 3.9 | As a candidate I should be able to delete my application for tasks/projects | 5 | Gabry | 3.7 | Shahd
| 3.10 | As a candidate I should view my notifications for projects I applied for to know if I am accepted | 5 | Gabry | 1.24 | Shahd
| 3.11 | As a candidate I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 13 | Gabry | 1.15 | Shahd
| 3.12 | As a candidate I should be able to search for certifications | 13 |  | 1.20
| 3.13 | As a candidate I should be able to view certifications so that I can apply for them | 5 | Gabry | 1.20 | Shahd
| 3.14 | As a candidate I should be able to apply for certificates so that I can get evaluated | 13 | Gabry | 1.20/3.13 | Shahd
| 3.15 | As a candidate who applied for certificates I should view notifications with details of evaluation process | 8 | Shahd | 1.20/1.24 | Farah
| 3.16 | As an accepted candidate for a certain project I should view my project orientation invitation | 5 | Ahmed Hossam | 1.28 | Farah
| 3.17 | As a candidate I should view certification recommendations so that I can apply for them | 13 |  | 1.20
| 3.18 | As a candidate I should be able to logout to leave my page | 3 |  | 3.2(not in this sprint)
Extra | 4.1 | As a candidate I should be able to view recommendation of projects that suit my skills | 13 |  | -