## Sheet1
| Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1.Admin | 1.1 | As an admin I should be able to sign in so that I can access my profile
| 1.2 | As an admin I should be able to view the project description so that I can approve/disapprove it getting posted | 8 | Peter | 2.3 | Farah
| 1.3 | As an admin I should be able to create tasks/projects so that candidates can apply | 8 | Peter | 2.3 | Farah
| 1.4 | As an admin I should be able to delete tasks | 5 | Peter | 2.3 | Farah
| 1.5 | As an admin I should be able to update tasks | 5 | Peter | 2.3 | Marwan
| 1.6 | As an admin I should be able to create project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 8 | Peter | 2.3 | Marwan
| 1.7 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 8 | Kariman | 2.3/1.6 | Marwan
| 1.8 | As an admin I should be able to read candidates' applications so that I can choose an appropriate candidate | 5 | Kariman | 3.7 | Marwan
| 1.9 | As an admin I should be able to assign tasks to appropriate candidates so that they get notified with the task | 8 | Kariman | 3.7 | Marwan
| 1.10 | As an admin I should be able to read the candidates' evaluation so that they check the authenticity | 5 | Kariman | 3.14 | Saad
| 1.11 | As an admin I should be able to update the candidates' evaluation so that they receive the certification | 8 | Kariman | 1.10 | Saad
| 1.12 | As an admin I should be able to view my profile | 5 | Karim | 1.1(not in this sprint) | Saad
| 1.13 | As an admin I should be able to update my profile | 8 | Karim | 1.1(not in this sprint) | Saad
| 1.14 | As an admin I should be able to delete my profile | 8 | Karim | 1.1(not in this sprint) | Saad
| 1.15 | As an admin I should be able to create project life cycle that includes all agreed upon steps so that the client views it everytime it gets updated | 8 | Karim | 1.9 | Ahmed Ashraf
| 1.16 | As an admin I should be able to create messages to partners so that we are able to negotiate project description | 8 | Karim | 2.3 | Ahmed Ashraf
| 1.17 | As an admin I should be able to view my messages | 5 | Ahmed Hossam | 1.16 | Ahmed Ashraf
| 1.18 | As an admin I should be able to delete inbox messages | 8 | Ahmed Hossam | 1.16/1.17/1.19 | Ahmed Ashraf
| 1.19 | As an admin I should be able to read messages from partners so that we are able to negotiate project description | 8 | Ahmed Hossam | 2.10 | Ahmed Ashraf
| 1.20 | As an admin I should be able to create evaluations for certificates | 3 | Ahmed Hossam | - | Gabry
| 1.21 | As an admin I should be able to view the evaluations for certificates | 5 | Ahmed Hossam | 1.20 | Gabry
| 1.22 | As an admin I should be able to update evaluations for certificates | 5 | Shahd | 1.20/1.21 | Gabry
| 1.23 | As an admin I should be able to delete evaluations for certificates | 5 | Shahd | 1.20/1.21 | Gabry
| 1.24 | As an admin I should be able to create notifications to candidates | 5 | Shahd | - | Gabry
| 1.25 | As an admin I should be able to delete notifications to candidates | 5 | Shahd | 1.24 | Islam
| 1.26 | As an admin I should be able to update notifications to candidates | 5 | Shahd | 1.24 | Islam
| 1.27 | As an admin I should be able to view notifications to candidates | 3 | Islam | 1.24 | Islam
| 1.28 | As an admin I should be able to create project orientation invitation to accepted candidates | 5 | Islam | 1.3 | Islam
| 1.29 | As an admin I should be able to update project orientation invitation to accepted candidates | 3 | Islam | 1.3/1.28 | Islam
| 1.30 | As an admin I should be able to delete project orientation invitation to accepted candidates | 5 | Islam | 1.3/1.28 | Shahd
| 1.31 | As an admin I should be able to view my project orientation invitation to accepted candidates | 3 | Islam | 1.3/1.28 | Shahd
| 1.32 | As an admin I should be able to logout to leave my page
2. PARTNER | 2.1 | As a partner I should be able to sign up so that I can create an account
| 2.2 | As a partner I should be able to sign in so that I can access my profile
| 2.3 | As a partner I should be able to create a project description so that it gets viewed by the admin | 5 | Gabry | - | Shahd
| 2.4 | As a partner I should be able to view my project description(s) | 3 | Gabry | 2.3 | Shahd
| 2.5 | As a partner I should be able to update my project description(s) | 5 | Gabry | 2.3 | Shahd
| 2.6 | As a partner I should be able to delete my project description(s) | 8 | Gabry | 2.3 | Ahmed Hossam
| 2.7 | As a partner I should be able to view my profile | 5 | Gabry | 2.2(not in this sprint) | Ahmed Hossam
| 2.8 | As a partner I should be able to update my profile | 8 | Ahmed Ashraf | 2.2(not in this sprint) | Ahmed Hossam
| 2.9 | As a partner I should be able to delete my profile | 8 | Ahmed Ashraf | 2.2(not in this sprint) | Ahmed Hossam
| 2.10 | As a partner I should be able to create messages to admins so that we are able to negotiate project description | 13 | Ahmed Ashraf | 2.3 | Ahmed Hossam
| 2.11 | As a partner I should be able to view my messages | 13 | Ahmed Ashraf | 2.10 | Karim
| 2.12 | As a partner I should be able to read messages from admins so that we are able to negotiate project description | 13 | Ahmed Ashraf | 1.16 | Karim
| 2.13 | As a partner I should be able to delete inbox messages | 8 | Saad | 2.10/2.11/2.12 | Karim
| 2.14 | As a partner I should be able to logout to leave my page
3. CANDIDATE | 3.1 | As a candidate I should be able to sign up so that I can create an account
| 3.2 | As a candidate I should be able to sign in so that I can access my profile
| 3.3 | As a candidate I should be able to view my profile | 5 | Saad | 3.2(not in this sprint) | Karim
| 3.4 | As a candidate I should be able to update my profile | 8 | Saad | 3.2(not in this sprint) | Karim
| 3.5 | As a candidate I should be able to delete my profile | 8 | Saad | 3.2(not in this sprint) | Kariman
| 3.6 | As a candidate I should be able to view tasks/projects to apply for them | 8 | Saad | 1.3 | Kariman
| 3.7 | As a candidate I should be able to apply for tasks/projects that fit my skills so that the admin views my application | 13 | Marwan | 1.3/3.6 | Kariman
| 3.8 | As a candidate I should be able to search for tasks so that I can apply for them
| 3.9 | As a candidate I should be able to delete my application for tasks/projects | 5 | Marwan | 3.7 | Kariman
| 3.10 | As a candidate I should view my notifications for projects I applied for to know if I am accepted | 5 | Marwan | 1.24 | Kariman
| 3.11 | As a candidate I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 13 | Marwan | 1.15 | Peter
| 3.12 | As a candidate I should be able to search for certifications
| 3.13 | As a candidate I should be able to view certifications so that I can apply for them | 5 | Marwan | 1.20 | Peter
| 3.14 | As a candidate I should be able to apply for certificates so that I can get evaluated | 13 | Farah | 1.20/3.13 | Peter
| 3.15 | As a candidate who applied for certificates I should view notifications with details of evaluation process | 8 | Farah | 1.20/1.24 | Peter
| 3.16 | As an accepted candidate for a certain project I should view my project orientation invitation | 5 | Farah | 1.28 | Peter
| 3.17 | As a candidate I should view certification recommendations so that I can apply for them
| 3.18 | As a candidate I should be able to logout to leave my page
| 3.19 | As a candidate I should be able to view recommendation of projects that suit my skills

## Sheet2
| Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1.Admin | 1.1
| 1.2 | As an admin I should be able to view the projects sorted by upload date | 8 |  | 2.3 | Farah
As an admin I should be able to view the project description to approve it to be posted
As an admin I should be able to view the project description to disapprove it
As an admin I should be able to search projects by project name
| 1.3 | As an admin I should be able to create tasks/projects so that candidates can apply | 8 | Peter | 2.3 | Farah
| 1.4 | As an admin I should be able to delete tasks | 5 | Peter | 2.3 | Farah
| 1.5 | As an admin I should be able to update tasks | 5 | Peter | 2.3 | Marwan
| 1.6 | As an admin I should be able to create project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 8 | Peter | 2.3 | Marwan
| 1.7 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 8 | Kariman | 2.3/1.6 | Marwan
| 1.8 | As an admin I should be able to read candidates' applications so that I can choose an appropriate candidate | 5 | Kariman | 3.7 | Marwan
| 1.9 | As an admin I should be able to assign tasks to appropriate candidates so that they get notified with the task | 8 | Kariman | 3.7 | Marwan
| 1.10 | As an admin I should be able to read the candidates' evaluation | 5 | Kariman | 3.14 | Saad
| 1.11 | As an admin I should be able to update the candidates' evaluation so that they receive the certification | 8 | Kariman | 1.10 | Saad
| 1.12 | As an admin I should be able to view my profile | 5 | Karim | 1.1(not in this sprint) | Saad
| 1.13 | As an admin I should be able to update my profile | 8 | Karim | 1.1(not in this sprint) | Saad
| 1.14 | As an admin I should be able to delete my profile | 8 | Karim | 1.1(not in this sprint) | Saad
| 1.15 | As an admin I should be able to create project life cycle that includes all agreed upon steps so that the client views it everytime it gets updated | 8 | Karim | 1.9 | Ahmed Ashraf
| 1.16 | As an admin I should be able to create messages to partners so that we are able to negotiate project description | 8 | Karim | 2.3 | Ahmed Ashraf
| 1.17 | As an admin I should be able to view my messages sorted by their receiving date | 5 | Ahmed Hossam | 1.16 | Ahmed Ashraf
| 1.18 | As an admin I should be able to delete inbox messages | 8 | Ahmed Hossam | 1.16/1.17/1.19 | Ahmed Ashraf
| 1.19 | As an admin I should be able to read messages from partners so that we are able to negotiate project description | 8 | Ahmed Hossam | 2.10 | Ahmed Ashraf
| 1.20 | As an admin I should be able to create evaluations for certificates | 3 | Ahmed Hossam | - | Gabry
| 1.21 | As an admin I should be able to view the evaluations for certificates | 5 | Ahmed Hossam | 1.20 | Gabry
| 1.22 | As an admin I should be able to update evaluations for certificates | 5 | Shahd | 1.20/1.21 | Gabry
| 1.23 | As an admin I should be able to delete evaluations for certificates | 5 | Shahd | 1.20/1.21 | Gabry
| 1.24 | As an admin I should be able to create notifications to candidates | 5 | Shahd | - | Gabry
| 1.25 | As an admin I should be able to delete notifications to candidates | 5 | Shahd | 1.24 | Islam
| 1.26 | As an admin I should be able to update notifications to candidates | 5 | Shahd | 1.24 | Islam
| 1.27 | As an admin I should be able to view notifications to candidates | 3 | Islam | 1.24 | Islam
| 1.28 | As an admin I should be able to create project orientation invitation to accepted candidates | 5 | Islam | 1.3 | Islam
| 1.29 | As an admin I should be able to update project orientation invitation to accepted candidates | 3 | Islam | 1.3/1.28 | Islam
| 1.30 | As an admin I should be able to delete project orientation invitation to accepted candidates | 5 | Islam | 1.3/1.28 | Shahd
| 1.31 | As an admin I should be able to view my project orientation invitation to accepted candidates | 3 | Islam | 1.3/1.28 | Shahd
As an admin I should be able to create certificates for candidates to apply
As an admin I should be able to view certificates by their category
As an admin I should be able to delete certificates
| 1.32 | As an admin I should be able to search all certificates by their category
2. PARTNER | 2.1 | As an admin I should be able to search all partners by their names
| 2.2 | As an admin I should be able to view partners sorted by registeration date
| 2.3 | As an admin I should be able to search all candidates by their names | 5 | Gabry | - | Shahd
| 2.4 | As an admin I should be able to view candidates sorted by registeration date | 3 | Gabry | 2.3 | Shahd
| 2.5 | As a partner I should be able to create a project description so that it gets viewed by the admin | 5 | Gabry | 2.3 | Shahd
| 2.6 | As a partner I should be able to view my projects | 8 | Gabry | 2.3 | Ahmed Hossam
| 2.7 | As a partner I should be able to update my project description before it gets approved | 5 | Gabry | 2.2(not in this sprint) | Ahmed Hossam
| 2.8 | As a partner I should be able to delete my project description before it gets approved | 8 | Ahmed Ashraf | 2.2(not in this sprint) | Ahmed Hossam
| 2.9 | As a partner I should be able to view my profile | 8 | Ahmed Ashraf | 2.2(not in this sprint) | Ahmed Hossam
| 2.10 | As a partner I should be able to update my profile | 13 | Ahmed Ashraf | 2.3 | Ahmed Hossam
| 2.11 | As a partner I should be able to delete my profile | 13 | Ahmed Ashraf | 2.10 | Karim
| 2.12 | As a partner I should be able to create messages to admins so that we are able to negotiate project description | 13 | Ahmed Ashraf | 1.16 | Karim
| 2.13 | As a partner I should be able to view my messages sorted by their receiving date | 8 | Saad | 2.10/2.11/2.12 | Karim
| 2.14 | As a partner I should be able to read messages from admins so that we are able to negotiate project description
3. CANDIDATE | 3.1 | As a partner I should be able to delete inbox messages
3.2
| 3.3 |  | 5 | Saad | 3.2(not in this sprint) | Karim
| 3.4 |  | 8 | Saad | 3.2(not in this sprint) | Karim
| 3.5 | As a candidate I should be able to view my profile | 8 | Saad | 3.2(not in this sprint) | Kariman
| 3.6 | As a candidate I should be able to update my profile | 8 | Saad | 1.3 | Kariman
| 3.7 | As a candidate I should be able to delete my profile | 13 | Marwan | 1.3/3.6 | Kariman
| 3.8 | As a candidate I should be able to view tasks/projects sorted by their posting date to apply for them
As a candidate I should be able to search all projects by their type so that I can apply for them
| 3.9 | As a candidate I should be able to apply for tasks/projects that fit my skills so that the admin views my application | 5 | Marwan | 3.7 | Kariman
| 3.10 | As a candidate I should be able to search for my tasks/projects by their type | 5 | Marwan | 1.24 | Kariman
| 3.11 | As a candidate I should be able to delete my application for tasks/projects | 13 | Marwan | 1.15 | Peter
| 3.12 | As a candidate I should view my notifications for projects I applied for to know if I am accepted
| 3.13 | As a candidate I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 5 | Marwan | 1.20 | Peter
| 3.14 | As a candidate I should be able to search for certifications by their category | 13 | Farah | 1.20/3.13 | Peter
| 3.15 | As a candidate I should be able to view certifications sorted by their category so that I can apply for them | 8 | Farah | 1.20/1.24 | Peter
| 3.16 | As a candidate I should be able to apply for certificates so that I can get evaluated | 5 | Farah | 1.28 | Peter
| 3.17 | As a candidate who applied for certificates I should view notifications with details of evaluation process
| 3.18 | As an accepted candidate for a certain project I should view my project orientation invitation
| 3.19 | As a candidate I should view certification recommendations so that I can apply for them
| 4.1 | As a consultant I should be able to apply only for the projects that requested by the partner to receive consulting
As a consultant I should be able to view the life cycle of the project I got assigned to so that I know the workflow
As a consultant I should be able to set a plan by viewing the project
As a consultant I should be able to choose which candidates, based on their set of skills, will be accepted for the project I got assigned to
As a consultant I should be able to set managerial roles (scrum master, manager, member) for the accepted candidates of the project I got assigned to
As a consultant I should be able to search all projects that need consulting by project type
As a consultant I should be able to view all projects that need consulting sorted by posting date
As a consultant I should be able to sign-up/create profile
As a consultant I should be able to sign-in/read/view my profile so that I can be redirected to it.
As a consultant I should be able to update my profile
As a consultant I should be able to delete my profile
As a consultant I should be able to create messages to admins/partners/candidates
As a consultant I should be able to view my messages sorted by their receiving date
As a consultant I should be able to delete inbox messages

## Sheet3
| Unique ID | User story | Story Points | Asignee | Reviewer 1 | Reviewer 2
1.Admin | 1.1 | As an admin I should be able to view the projects sorted by upload date | 5 | Farah | shahd | kariman
| 1.2 | As an admin I should be able to approve projects to be posted | 8 | Marawan | Gabry | Ashraf
| 1.3 | As an admin I should be able to disapprove projects | 8 | Marawan | Gabry | Ashraf
| 1.4 | As an admin I should be able to create tasks/projects so that candidates can apply | 5 | deleted
| 1.5 | As an admin I should be able to delete projects | 5 | deleted
| 1.6 | As an admin I should be able to update projects | 5 | deleted
| 1.7 | As an admin I should be able to create project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | postponed
| 1.8 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | postponed
| 1.9 | As an admin I should be able to view candidates' applications so that I can choose an appropriate candidate | 5 | postponed
| 1.10 | As an admin I should be able to assign tasks to appropriate candidates so that they get notified with the task | 8 | postponed
| 1.11 | As an admin I should be able to view the candidates' evaluation | 5 | postponed
| 1.12 | As an admin I should be able to view my profile | 5 | Farah | shahd | kariman
| 1.13 | As an admin I should be able to update my profile | 5 | Farah | shahd | kariman
| 1.14 | As an admin I should be able to delete my profile | 5 | Farah | shahd | kariman
| 1.15 | As an admin I should be able to create project life cycle that includes all agreed upon steps so that the client views it everytime it gets updated | 5 | postponed
| 1.16 | As an admin I should be able to create messages to partners so that we are able to negotiate project description | 5 | Peter | Hossam | Karim
| 1.17 | As an admin I should be able to view my messages sorted by their receiving date | 5 | Peter | Hossam | Karim
| 1.18 | As an admin I should be able to delete inbox messages | 5 | Peter | Hossam | Karim
| 1.19 | As an admin I should be able to read messages from partners so that we are able to negotiate project description | 5 | Peter | Hossam | Karim
| 1.20 | As an admin I should be able to create evaluations for certificates | 5 | Islam | farah | Saad
| 1.21 | As an admin I should be able to view the evaluations for certificates | 5 | Islam | farah | saad
| 1.22 | As an admin I should be able to update evaluations for certificates | 5 | deleted
| 1.23 | As an admin I should be able to delete evaluations for certificates | 5 | Saad | islam | farah
| 1.24 | As an admin I should be able to create notifications to candidates | 5 | deleted
| 1.25 | As an admin I should be able to delete notifications to candidates | 5 | deleted
| 1.26 | As an admin I should be able to update notifications to candidates | 5 | deleted
| 1.27 | As an admin I should be able to view notifications to candidates | 5 | deleted
| 1.28 | As an admin I should be able to create project orientation invitation to accepted candidates | 5 | postponed
| 1.29 | As an admin I should be able to update project orientation invitation to accepted candidates | 5 | deleted
| 1.30 | As an admin I should be able to delete project orientation invitation to accepted candidates | 5 | deleted
| 1.31 | As an admin I should be able to view my project orientation invitation to accepted candidates | 5 | Saad | islam | farah
| 1.32 | As an admin I should be able to create certificates for candidates to apply | 5 | Islam | farah | saad
| 1.33 | As an admin I should be able to view certificates by their category | 5 | Islam | farah | saad
| 1.34 | As an admin I should be able to delete certificates | 5 | Islam | farah | saad
| 1.35 | As an admin I should be able to notify candidates of their evaluation score so that they know if they received the certificate | 8 | Saad | islam | farah
| 1.36 | As an admin I should be able to add a certificate to candidates' profiles if they passed the evaluation | 8 | postponed
2. PARTNER | 2.1 | As a partner I should be able to sign up | 5 | Kariman | shahd | farah
| 2.2 | As a partner I should be able to view my profile | 5 | Kariman | shahd | farah
| 2.3 | As a partner I should be able to update my profile | 5 | Kariman | shahd | farah
| 2.4 | As a partner I should be able to delete my profile | 5 | Shahd | peter | islam
| 2.5 | As a partner I should be able to create messages to admins so that we are able to negotiate project description | 5 | Karim | Hossam | peter
| 2.6 | As a partner I should be able to view my messages sorted by their receiving date | 8 | Karim | Hossam | peter
| 2.7 | As a partner I should be able to read messages from admins so that we are able to negotiate project description | 5 | Karim | Hossam | peter
| 2.8 | As a partner I should be able to delete inbox messages | 5 | Karim | Hossam | peter
| 2.9 | As a partner I should be able to create a project description so that it gets viewed by the admin | 5 | Shahd | kariman | farah
| 2.10 | As a partner I should be able to view my projects sorted by their upload date | 5 | Shahd | karmian | farah
| 2.11 | As a partner I should be able to update my project description before it gets approved | 8 | Shahd | karmian | farah
| 2.12 | As a partner I should be able to delete my project description before it gets approved | 8 | Shahd | karmian | farah
3. CANDIDATE | 3.1 | As a candidate I should be able to sign up | 5 | Hossam | peter | karim
| 3.2 | As a candidate I should be able to view my profile | 5 | Hossam | peter | karim
| 3.3 | As a candidate I should be able to update my profile | 5 | Peter | Hossam | karim
| 3.4 | As a candidate I should be able to delete my profile | 5 | Peter | Hossam | karim
| 3.5 | As a candidate I should be able to view tasks/projects sorted by their posting date to apply for them | 8 | Saad | farah | islam
| 3.6 | As a candidate I should be able to delete my application for tasks/projects before they get approved | 8 | postponed
| 3.7 | As a candidate I should view my notifications for projects I applied for to know if I am accepted | 5 | postponed
| 3.8 | As a candidate I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 5 | Ashraf | Gabry | marwan
| 3.9 | As a candidate I should be able to view certifications sorted by their category so that I can apply for them | 8 | Ashraf | Gabry | marwan
| 3.10 | As a candidate who applied for certificates I should view notifications with details of evaluation process | 5 | Ashraf | Gabry | marwan
| 3.11 | As an accepted candidate for a certain project I should view my project orientation invitation | 5 | Ashraf | Gabry | marwan
4. Consultancy | 4.1 | As a consultant I should be able to create profile | 8 | Kariman | shahd | farah
| 4.2 | As a consultant I should be able to view my profile | 8 | Kariman | shahd | farah
| 4.3 | As a consultant I should be able to update my profile | 8 | Karim | Hossam | peter
| 4.4 | As a consultant I should be able to delete my profile | 8 | Marawan | gabry | ashraf
| 4.5 | As a consultant I should be able to create messages to admins/partners/candidates | 8 | Hossam | peter | karim
| 4.6 | As a consultant I should be able to view my messages sorted by their receiving date | 8 | Hossam | peter | karim
| 4.7 | As a consultant I should be able to delete inbox messages | 8 | Hossam | peter | karim
| 4.8 | As a consultant I should be able to apply only for the projects that requested by the partner to receive consulting | 8 | Ashraf | Gabry | marwan
| 4.9 | As a consultant I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 8 | Gabry | Ashraf | marwan
| 4.10 | As a consultant I should be able to set a plan by viewing the project | 8 | Gabry | Ashraf | mawan
| 4.11 | As a consultant I should be able to choose which candidates, based on their set of skills, will be accepted for the project I got assigned to | 8 | Gabry | Ashraf | marwan
| 4.12 | As a consultant I should be able to set managerial roles (scrum master, manager, member) for the accepted candidates of the project I got assigned to | 8 | Gabry | Ashraf | marwan
| 4.13 | As a consultant I should be able to view all projects that need consulting sorted by posting date | 8 | Gabry | Ashraf | marwan