## Sheet1
| Unique ID | User story | Story Points | Asignee | Reviewer 1 | Reviewer 2
1. Admin | 1.1 | As an admin I should be able to sign in so that I can access my profile | 5 | Marwan | Ashraf | Gabry
| 1.2 | As an admin I should be able to create project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | Gabry | Ashraf | Marwan
| 1.3 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | Ashraf | Gabry | Marwan
| 1.4 | As an admin I should be able to search projects by project name | 5 | Gabry | Ashraf | Marwan
| 1.5 | As an admin I should be able to view candidates' applications so that I can choose an appropriate candidate | 5 | Ashraf | Gabry | Gabry
| 1.6 | As an admin I should be able to assign tasks to appropriate candidates so that they get notified with the task | 5 | Gabry | Ashraf | Marwan
| 1.7 | As an admin I should be able to view the candidates' evaluation | 5 | Karim | Peter | Hossam
| 1.8 | As an admin I should be able to create project life cycle that includes all agreed upon steps so that the client views it everytime it gets updated | 5 | Karim | Peter | Hossam
| 1.9 | As an admin I should be able to create project orientation invitation to accepted candidates | 5 | Hossam | Peter | Karim
| 1.10 | As an admin I should be able to add a certificate to candidates' profiles if they passed the evaluation | 5 | Islam | Omar | Farah
| 1.11 | As an admin I should be able to search all partners by their names | 5 | Hossam | Marwan | Islam
| 1.12 | As an admin I should be able to view partners sorted by registeration date | 5 | Shahd | Kariman | Farah
| 1.13 | As an admin I should be able to search all candidates by their names | 5 | Shahd | Kariman | Farah
| 1.14 | As an admin I should be able to view candidates sorted by registeration date | 5 | Shahd | Kariman | Farah
| 1.15 | As an admin I should be able to logout to leave my page | 5 | Kariman | Shahd | Farah
2. Partner | 2.1 | As a partner I should be able to sign in so that I can access my profile | 5 | Kariman | Shahd | Farah
| 2.2 | As a partner I should be able to logout to leave my page | 5 | Kariman | Shahd | Farah
3. Candidate | 3.1 | As a candidate I should be able to sign in so that I can access my profile | 5 | Kariman | Shahd | Farah
| 3.2 | As a candidate I should be able to view tasks/projects sorted by their posting date to apply for them | 5 | Shahd | Kariman | Farah
| 3.3 | As a candidate I should be able to apply for tasks/projects that fit my skills so that the admin views my application | 5 | Karim | Hossam | Peter
| 3.4 | As a candidate I should be able to search for my tasks/projects by their name | 5 | Karim | Hossam | Peter
| 3.5 | As a candidate I should be able to delete my application for tasks/projects before they get approved | 5 | Hossam | Karim | Peter
| 3.6 | As a candidate I should view my messages for projects I applied for to know if I am accepted | 5 | Hossam | Karim | Peter
| 3.7 | As a candidate I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 5 | Peter | Hossam | Karim
| 3.8 | As a candidate I should be able to view certifications sorted by their category so that I can apply for them | 5 | Peter | Hossam | Karim
| 3.9 | As a candidate I should be able to apply for certificates so that I can get evaluated | 5 | Peter | Hossam | Karim
| 3.10 | As a candidate who applied for certificates I should view messages with details of evaluation process | 5 | Peter | Hossam | Karim
| 3.11 | As an accepted candidate for a certain project I should view my project orientation invitation | 5 | Marwan | Omar | Islam
| 3.12 | As a candidate I should be able to search for certificates by their name | 5 | Ashraf | Gabry | Karim
4. Consultancy | 4.1 | As a consultant I should be able to apply only for the projects that requested by the partner to receive consulting | 5 | Marwan | Omar | Islam
| 4.2 | As a consultant I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 5 | Omar | Marwan | Islam
| 4.3 | As a consultant I should be able to set a plan by viewing the project | 5 | Islam | Omar | Marwan
| 4.4 | As a consultant I should be able to choose which candidates, based on their set of skills, will be accepted for the project I got assigned to | 5 | Marwan | Omar | Islam
| 4.5 | As a consultant I should be able to set managerial roles (scrum master, manager, member) for the accepted candidates of the project I got assigned to | 5 | Islam | Omar | Marwan
| 4.6 | As a consultant I should be able to view all projects that need consulting sorted by posting date | 5 | Omar | Islam | Marwan
| 4.7 | As a consultant I should be able to apply only for the projects that requested by the partner to receive consulting | 5 | Omar | Islam | Marwan
| 4.8 | As a consultant I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 5 | Islam | Omar | Marwan
| 4.9 | As a consultant I should be able to set a plan by viewing the project | 5 | Farah | Karim | Hossam
| 4.10 | As a consultant I should be able to choose which candidates, based on their set of skills, will be accepted for the project I got assigned to | 5 | Omar | Peter | Hossam
| 4.11 | As a consultant I should be able to set managerial roles (scrum master, manager, member) for the accepted candidates of the project I got assigned to | repeated | Farah | Omar | Islam
| 4.12 | As a consultant I should be able to view all projects that need consulting sorted by posting date | 5 | Farah | Omar | Islam