## Sheet1
| Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1.ADMIN | 1.2 | As an admin I should be able to create a project using description so that candidates can apply for it. | 8 | Karim | 2.3 | Islam
| 1.3 | As an admin I should be able to read a project description so that I can approve or disapprove it. | 8 | Karim | 2.3 | Islam
| 1.4 | As an admin I should be able to update a project description so that I aprrove the reviewed changes. | 5 | Karim | 2.3 | Islam
| 1.5 | As an admin I should be able to delete a project so that so that I can remove the whole project. | 5 | Karim | 2.3 | Islam
| 1.6 | As an admin I should be able to create/assign project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it. | 8 | Peter | 2.3 | Islam
| 1.7 | As an admin I should be able to read project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that I can review it. | 8 | Peter | 2.3 | Islam
|  | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it. | 8 | Peter | 2.3 | Islam
|  | As an admin I should be able to delete project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that I can remove the whole project. | 8 | Peter | 2.3 | Islam
| 1.8 | As an admin I should be able to view applied candidates' profiles so that I can choose the appropriate one for the project. | 5 | Peter | 3.7 | Farah
| 1.9 | As an admin I should be able to assign the project to the chosen candidate/candidates so that a notification message to be sent to them. | 8 | Peter | 3.7 | Farah
|  | As an admin I should be able to create a certification test for the applied candidates so that they can be evaluated. | 5 | Peter | 3.14 | Gabry
| 1.10 | As an admin I should be able to read the applied candidates' certification test results so that I can evaluate them. | 5 | Peter | 3.14 | Gabry
| 1.11 | As an admin I should be able to update the candidates' with the evaluation results so that they receive a success notification message and show it on his profile. | 8 | Karim | 3.14 | Gabry
|  | As an admin I should be able to delete the applied candidates' certification tests so that they receive a fail notification message. | 8 | Karim | 3.14 | Gabry
As an admin I should be able to sign-up/create one unique profile so that I can start using all my authorities.
As an admin I should be able to sign-in/read/view my profile so that I can be redirected to it.
As an admin I should be able to update my profile so that I can edit my personal information.
As an admin I should be able to delete my profile so that I can quit my job.
As an admin I should be able to sign-out.
As an admin I should be able to search all the projects
As an admin I should be able to search all the certifications
As an admin I should be able to search all the partners
As an admin I should be able to search all the candidates
| 1.15 | As an admin I should be able to create project life cycle. | 8 | Ahmed Hossam | 1.9 | Karim
|  | As an admin I should be able to read project life cycle so that I can check it. | 8 | Ahmed Hossam | 1.15 | Karim
|  | As an admin I should be able to update project life cycle so that I can edit it with new steps. | 8 | Ahmed Hossam | 1.15 | Karim
|  | As an admin I should be able to delete project life cycle so that I can remove the whole project. | 8 | Ahmed Hossam | 1.15 | Karim
| 1.16 | As an admin I should be able to create/send/receive messages to partners/candidates so that I can notify them with anything I want. | 8 | Saad | - | Karim
| 1.17 | As an admin I should be able to read/receive any message from my inbox so that I can be notified with anything. | 5 | Saad | 1.16 | Karim
| 1.18 | As an admin I should be able to update/refresh my inbox. | 8 | Saad | 1.16 | Karim
| 1.19 | As an admin I should be able to delete any message from my inbox. | 8 | Saad | 1.16 | Karim
| 1.28 | As an admin I should be able to create/send project orientation invitation to the accepted candidate/candidates and the partner associated to the project. | 5 | Shahd | 1.2 | Marwan
| 1.29 | As an admin I should be able to read project orientation invitation to accepted candidates so that I can schedule it. | 3 | Shahd | 1.28 | Marwan
| 1.30 | As an admin I should be able to update project orientation invitation to accepted candidates so that I can change any information within the invitation. | 5 | Shahd | 1.28 | Marwan
| 1.31 | As an admin I should be able to delete my project orientation invitation to accepted candidates so that I can remove the whole project. | 3 | Shahd | 1.28 | Marwan
2. PARTNER |  | As a partner I should be able to sign-up/create profile so that I can start using all my authorities.
As a partner I should be able to sign-in/read/view my profile so that I can be redirected to it.
As a partner I should be able to update my profile so that I can edit my personal information.
As a partner I should be able to delete my profile so that I can stop using the website.
As a partner I should be able to sign-out.
| 2.3 | As a partner I should be able to create/submit a new project with its description so that it can be reviewed by the admin. | 5 | Islam | - | Ahmed Ashraf
| 2.4 | As a partner I should be able to read my project description. | 3 | Islam | 2.3 | Ahmed Ashraf
| 2.5 | As a partner I should be able to update my project description so that I can edit reviewed information from the admin. | 5 | Islam | 2.3 | Ahmed Ashraf
| 2.6 | As a partner I should be able to delete my project. | 8 | Islam | 2.3 | Ahmed Ashraf
| 2.10 | As a partner I should be able to create/send/receive messages to admins/candidates so that I can negotiate my project. | 13 | Kariman |  | Ahmed Hossam
| 2.11 | As a partner I should be able to read/receive any message from my inbox so that I can be notified with anything. | 13 | Kariman |  | Ahmed Hossam
| 2.12 | As a partner I should be able to update/refresh my inbox. | 13 | Islam |  | Ahmed Hossam
| 2.13 | As a partner I should be able to delete any message from my inbox. | 8 | Saad |  | Farah
3.CANDIDATE |  | As a candidate I should be able to sign-up/create profile so that I can start using all my authorities.
As a candidate I should be able to sign-in/read/view my profile so that I can be redirected to it.
As a candidate I should be able to update my profile so that I can edit my personal information.
As a candidate I should be able to delete my profile so that I can stop using the website.
As a candidate I should be able to sign-out.
As a candidate I should be able to search all uploaded tasks by the admin.
As a candidate I should be able to search all the certifications.
| 3.7 | As a candidate I should be able to apply only for the projects that fit my profile set of skills. | 13 | Farah | 1.3/3.6 | Kariman
| 3.9 | As a candidate I should be able to delete/apologize my request to do the project after I got accepted from the admin. | 5 | Gabry | 3.7 | Shahd
| 3.11 | As a candidate I should be able to read the life cycle of the project I got assigned to so that I know the workflow. | 13 | Gabry | 1.15 | Shahd
| 3.14 | As a candidate I should be able to apply only for the certificates that are not present in my profile set of skills
As a candidate I should be able to create/send/receive messages to admins/partners so that I can notify them with anything.
As a candidate I should be able to read/receive any message from my inbox so that I can be notified with anything.
As a candidate I should be able to update/refresh my inbox.
As a candidate I should be able to delete any message from my inbox.
Extra | 4.1 | As a candidate I should be able to see a recommendations list that shows the projects that suit my profile set of skills.
Extra | 4.2 | As a candidate I should be able to see a recommendations list that shows the certifications that would boost my profile set of skills.