## Sheet3
| Unique ID | User story | Story Points | Asignee | Reviewer 1 | Reviewer 2
1.Admin | 1.01 | As an admin I should be able to view the projects sorted by upload date | 5 | Peter | Islam | Peter
| 1.02 | As an admin I should be able to approve projects to be posted | 8 | Peter | Shahd | Peter
| 1.03 | As an admin I should be able to disapprove projects | 8 | Peter | Kariman | Peter
| 1.04 | As an admin I should be able to create tasks/projects so that candidates can apply | 5 | Peter | Hossam | Peter
| 1.05 | As an admin I should be able to delete projects | 5 | Peter | Karim | Peter
| 1.06 | As an admin I should be able to update projects | 5 | Peter | Peter | Peter
| 1.07 | As an admin I should be able to create project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | Karim | Marwan | Karim
| 1.08 | As an admin I should be able to update project attributes (effort level, delivery time, commitment level, experience level,set of skills needed,cost,partner info,specific consultancy etc) so that candidates can apply for it | 5 | Karim | Marwan | Karim
| 1.09 | As an admin I should be able to view candidates' applications so that I can choose an appropriate candidate | 5 | Karim | Marwan | Karim
| 1.1 | As an admin I should be able to assign tasks to appropriate candidates so that they get notified with the task | 8 | Karim | Marwan | Karim
| 1.11 | As an admin I should be able to view the candidates' evaluation | 5 | Karim | Marwan | Karim
| 1.12 | As an admin I should be able to view my profile | 5 | Karim | Marwan | Karim
| 1.13 | As an admin I should be able to update my profile | 5 | Hossam | Ashraf | Hossam
| 1.14 | As an admin I should be able to delete my profile | 5 | Hossam | Ashraf | Hossam
| 1.15 | As an admin I should be able to create project life cycle that includes all agreed upon steps so that the client views it everytime it gets updated | 5 | Hossam | Ashraf | Hossam
| 1.16 | As an admin I should be able to create messages to partners so that we are able to negotiate project description | 5 | Hossam | Ashraf | Hossam
| 1.17 | As an admin I should be able to view my messages sorted by their receiving date | 5 | Hossam | Ashraf | Hossam
| 1.18 | As an admin I should be able to delete inbox messages | 5 | Hossam | Ashraf | Hossam
| 1.19 | As an admin I should be able to read messages from partners so that we are able to negotiate project description | 5 | Kariman | Gabry | Kariman
| 1.2 | As an admin I should be able to create evaluations for certificates | 5 | Kariman | Gabry | Kariman
| 1.21 | As an admin I should be able to view the evaluations for certificates | 5 | Kariman | Gabry | Kariman
| 1.22 | As an admin I should be able to update evaluations for certificates | 5 | Kariman | Gabry | Kariman
| 1.23 | As an admin I should be able to delete evaluations for certificates | 5 | Kariman | Gabry | Kariman
| 1.24 | As an admin I should be able to create notifications to candidates | 5 | Kariman | Gabry | Kariman
| 1.25 | As an admin I should be able to delete notifications to candidates | 5 | Shahd | Farah | Shahd
| 1.26 | As an admin I should be able to update notifications to candidates | 5 | Shahd | Farah | Shahd
| 1.27 | As an admin I should be able to view notifications to candidates | 5 | Shahd | Farah | Shahd
| 1.28 | As an admin I should be able to create project orientation invitation to accepted candidates | 5 | Shahd | Farah | Shahd
| 1.29 | As an admin I should be able to update project orientation invitation to accepted candidates | 5 | Shahd | Farah | Shahd
| 1.3 | As an admin I should be able to delete project orientation invitation to accepted candidates | 5 | Shahd | Farah | Shahd
| 1.31 | As an admin I should be able to view my project orientation invitation to accepted candidates | 5 | Islam | Omar | Islam
| 1.32 | As an admin I should be able to create certificates for candidates to apply | 5 | Islam | Omar | Islam
| 1.33 | As an admin I should be able to view certificates by their category | 5 | Islam | Omar | Islam
| 1.34 | As an admin I should be able to delete certificates | 5 | Islam | Omar | Islam
| 1.35 | As an admin I should be able to notify candidates of their evaluation score so that they know if they received the certificate | 8 | Islam | Omar | Islam
| 1.36 | As an admin I should be able to add a certificate to candidates' profiles if they passed the evaluation | 8 | Islam | Omar | Islam
2. PARTNER | 2.01 | As a partner I should be able to sign up | 5 | Omar | Islam | Omar
| 2.02 | As a partner I should be able to view my profile | 5 | Omar | Islam | Omar
| 2.03 | As a partner I should be able to update my profile | 5 | Omar | Islam | Omar
| 2.04 | As a partner I should be able to delete my profile | 5 | Omar | Islam | Omar
| 2.05 | As a partner I should be able to create messages to admins so that we are able to negotiate project description | 5 | Omar | Islam | Omar
| 2.06 | As a partner I should be able to view my messages sorted by their receiving date | 8 | Omar | Islam | Omar
| 2.07 | As a partner I should be able to read messages from admins so that we are able to negotiate project description | 5 | Farah | Shahd | Farah
| 2.08 | As a partner I should be able to delete inbox messages | 5 | Farah | Shahd | Farah
| 2.09 | As a partner I should be able to create a project description so that it gets viewed by the admin | 5 | Farah | Shahd | Farah
| 2.1 | As a partner I should be able to view my projects sorted by their upload date | 5 | Farah | Shahd | Farah
| 2.11 | As a partner I should be able to update my project description before it gets approved | 8 | Farah | Shahd | Farah
| 2.12 | As a partner I should be able to delete my project description before it gets approved | 8 | Farah | Shahd | Farah
3. CANDIDATE | 3.01 | As a candidate I should be able to sign up | 5 | Gabry | Kariman | Gabry
| 3.02 | As a candidate I should be able to view my profile | 5 | Gabry | Kariman | Gabry
| 3.03 | As a candidate I should be able to update my profile | 5 | Gabry | Kariman | Gabry
| 3.04 | As a candidate I should be able to delete my profile | 5 | Gabry | Kariman | Gabry
| 3.05 | As a candidate I should be able to view tasks/projects sorted by their posting date to apply for them | 8 | Gabry | Kariman | Gabry
| 3.06 | As a candidate I should be able to delete my application for tasks/projects before they get approved | 8 | Gabry | Kariman | Gabry
| 3.07 | As a candidate I should view my notifications for projects I applied for to know if I am accepted | 5 | Ashraf | Hossam | Ashraf
| 3.08 | As a candidate I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 5 | Ashraf | Hossam | Ashraf
| 3.09 | As a candidate I should be able to view certifications sorted by their category so that I can apply for them | 8 | Ashraf | Hossam | Ashraf
| 3.1 | As a candidate who applied for certificates I should view notifications with details of evaluation process | 5 | Ashraf | Hossam | Ashraf
| 3.11 | As an accepted candidate for a certain project I should view my project orientation invitation | 5 | Ashraf | Hossam | Ashraf
4. Consultancy | 4.01 | As a consultant I should be able to create profile | 8 | Ashraf | Hossam | Ashraf
| 4.02 | As a consultant I should be able to view my profile | 8 | Marwan | Karim | Marwan
| 4.03 | As a consultant I should be able to update my profile | 8 | Marwan | Karim | Marwan
| 4.04 | As a consultant I should be able to delete my profile | 8 | Marwan | Karim | Marwan
| 4.05 | As a consultant I should be able to create messages to admins/partners/candidates | 8 | Marwan | Karim | Marwan
| 4.06 | As a consultant I should be able to view my messages sorted by their receiving date | 8 | Marwan | Karim | Marwan
| 4.07 | As a consultant I should be able to delete inbox messages | 8 | Marwan | Karim | Marwan
| 4.08 | As a consultant I should be able to apply only for the projects that requested by the partner to receive consulting | 8 | Peter | Peter | Peter
| 4.09 | As a consultant I should be able to view the life cycle of the project I got assigned to so that I know the workflow | 8 | Karim | Peter | Karim
| 4.1 | As a consultant I should be able to set a plan by viewing the project | 8 | Hossam | Peter | Hossam
| 4.11 | As a consultant I should be able to choose which candidates, based on their set of skills, will be accepted for the project I got assigned to | 8 | Kariman | Peter | Kariman
| 4.12 | As a consultant I should be able to set managerial roles (scrum master, manager, member) for the accepted candidates of the project I got assigned to | 8 | Shahd | Peter | Shahd
| 4.13 | As a consultant I should be able to view all projects that need consulting sorted by posting date | 8 | Islam | Peter | Islam